## Checklist
UV printing machine production acceptance checklist
From "How to Evaluate a UV Printing Machine: A Production Acceptance Checklist", https://www.protechnology.ae/uv-printing-machine-acceptance-checklist. Criteria values are agreed between buyer and supplier for your product before the trial. Record results, sample IDs and the instrument used. Use one copy for the print trial and another for site acceptance. Where a row covers several checks, record each result and mark Fail if any one fails. A check described as based on a standard is not a test to that standard unless its full procedure, equipment and conditions were followed. Brand-neutral; not a test report.
Step | Item to verify | Method or evidence | Criterion to agree | Agreed value | What to record | Recorded result | Pass / Fail / Not tested | Checked by | Date
1. Application | Substrate and coating | Material supplier specification and batch numbers | Application specification signed by buyer and supplier |  | Batch numbers tested
1. Application | Geometry and print area | Drawing or sample with dimensions | Print area and tolerances defined |  | Drawing reference
1. Application | Artwork and finish | Production files, test file and approved sample | Approved sample signed |  | File versions and sample ID
1. Application | Handling and exposure | List of filling, packing, transport and use conditions | Each exposure linked to a test |  | Reference to the list
2. Trial | Representative materials | Pieces from at least two batches where possible, at production temperature | Batches named in the test plan |  | Quantity per batch, item temperature
2. Trial | Delivered configuration | Ink set, primer, pre-treatment, print mode, curing and fixtures as quoted | Matches the quotation |  | Configuration list, pre-treatment interval
2. Trial | Fixtures | Production fixture used; every position checked for placement and height | Same placement and height in every position |  | Fixture ID and positions checked
2. Trial | Criteria agreed in advance | Test plan signed before printing | Plan signed before the run |  | Date signed
3. Output | Print cycle time | Stopwatch timing of several cycles on the production artwork, every layer included | At or below the agreed time |  | Average of timed cycles
3. Output | Machine cycle time | Timing from the start of one cycle to the start of the next, including loading | At or below the agreed time |  | Measured value, operator time per cycle
3. Output | Non-printing time | Log of start-up, checks, cleaning, changeovers and stops | Within the agreed allowance |  | Minutes per activity
3. Output | Accepted output per hour | Accepted pieces per shift, projected from the timed run and logged stops, divided by the shift hours | At or above the required figure |  | Pieces per hour and reject rate
3. Output | Ink use per piece | A full fixture weighed before and after printing, and refills measured over the run | Within the cost model assumption |  | Millilitres or grams per piece
4. Print quality | Small text and fine lines | Test file inspected with a magnifier | Smallest required size legible |  | Smallest size that passed
4. Print quality | Colour | Spectrophotometer, stated measurement condition and backing, CIEDE2000 | Maximum agreed difference from the approved sample |  | Difference per patch and instrument used
4. Print quality | White opacity and registration | Comparison with the approved sample; offsets measured with a measuring magnifier or callipers | No more show-through than the sample; offsets within the agreed millimetres |  | Observations and offsets per position
4. Print quality | Gloss, seam, texture, codes and defects | Inspection under controlled lighting; gloss meter, height gauge and scanner where needed | As agreed against the approved sample |  | Defects found, readings, scan results
5. Durability | Adhesion | Cross-cut and tape check based on ISO 2409 on the solid patch, after the agreed wait | Agreed classification, or no removal |  | Result, failure location, cure-to-test time
5. Durability | Abrasion and rub | Rub or handling test on the actual item | No visible wear after the agreed cycles |  | Cycles, load and observations
5. Durability | Chemical resistance | Contact, immersion or solvent rub with the named product | No softening, staining or transfer after the agreed exposure |  | Product, time, temperature and result
5. Durability | Water and condensation | Soak, chilled storage or condensation exposure as in use, then a repeat adhesion check | No softening or lifting after the agreed exposure |  | Conditions and result
5. Durability | Washing | Real wash cycles on the actual item | No visible change after the agreed number of cycles |  | Cycles, machine, detergent and result
5. Durability | Light and weathering | Agreed hours under a named laboratory method, compared with an unexposed sample | Colour change within the agreed limit |  | Method, hours and result
5. Durability | Heat and temperature change | Test at the real temperatures and durations of use | No visible change after the agreed exposure |  | Temperatures, durations and result
6. Repeatability | Within the run | First, middle and last pieces from each position compared with the approved sample; nozzle checks kept | All within the criteria |  | Sample IDs and results
6. Repeatability | After a stop and restart | First pieces after a planned stop, routine start-up only | Within the criteria, white included |  | Result after restart
6. Repeatability | Between batches and operators | Each batch printed; second operator runs from the recipe | Within the criteria |  | Batch, operator and result
6. Repeatability | UV dose | Radiometer reading at the print position, or an agreed cure check | Within the agreed range of the trial baseline |  | Readings, instrument and lamp hours
7. Operating requirements | Site readiness | Site requirements sheet for the exact model, checked on site | Every item signed off before installation |  | Signed sheet reference
7. Operating requirements | Ventilation and safety | Safety data sheets; extraction, guards, interlocks and UV shielding checked | Meets the documents and local rules |  | Who checked, and when
7. Operating requirements | Maintenance and consumables | Schedule and parts list reviewed; daily maintenance timed | Matches the plan and the cost model |  | Minutes per day
7. Operating requirements | Service and spares | Written service terms and spares list | Agreed in writing |  | Document references
8. Acceptance and handover | Site acceptance run | Key output, quality and durability checks repeated after installation, with a full-shift output run | Same criteria as the trial |  | Results and date
8. Acceptance and handover | Training and competence | Each operator runs the acceptance job and daily maintenance unaided | Every named operator passes |  | Names and dates
8. Acceptance and handover | Documents handed over | Handover file checked against the list in Step 8 | Complete |  | Missing items
8. Acceptance and handover | Operator and maintenance manuals | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Safety data sheets, current revisions | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Maintenance schedule, consumables list and spare parts | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Warranty terms, start date, service contacts and response arrangements | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Software licences and backups of profiles, modes and recipes | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Training records and competence checks | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Signed site requirements, acceptance record and approved samples | Present in the handover file | Present and current |  | Reference or version
8. Acceptance and handover | Sign-off | Acceptance record signed by both parties, with open items listed | Signed |  | Date and signatories
Sign-off
Buyer: name, role, signature, date
Supplier: name, role, signature, date
Open items and agreed actions

## Trial record
Trial and acceptance configuration record
Record exactly what was tested, so the configuration that passed can be repeated, and re-tested when it changes.
Field | Value
Machine model
Serial number
Firmware version
RIP (raster image processor) software and version
Ink series and batch numbers
Primer or pre-treatment, settings and interval before printing
Print mode(s) and resolution
Print height above the item
Curing settings, lamp type and lamp hours
Measured UV dose and intensity (instrument)
Fixtures and positions
Colour profile
Artwork files and versions
Substrate, material supplier and batch numbers
Item temperature when printed
Approved sample IDs and measured values
Approved samples: who holds them and storage conditions
Trial date and location
Operators
Room temperature and humidity
Materials supplied by
Results judged by, including borderline results
Number of samples per test
Cure-to-test time before durability tests
Measuring instruments (model and serial)
Witnesses (buyer and supplier)
Dispute and re-test procedure
Retest triggers agreed

## Output calculator
Accepted output calculator
HYPOTHETICAL example values from the guide (two fixtures loaded alternately, one operator). They are not measurements of any machine. Replace the yellow inputs with values timed in your own trial. For the one-fixture case, set fixtures to 1 and the swap time to 0.
Input or result | Value | Note
Fixtures used alternately (1 or 2) | 2 | Input
Pieces per fixture or load | 24 | Input
Print and cure time per load, every layer included (min) | 9 | Input
Load and unload one fixture (min) | 6 | Input
Inspect one load (min) | 2 | Input
Swap fixtures, machine waiting (min) | 1 | Input: 0 with one fixture
Shift length (min) | 480 | Input
Start-up, nozzle check and end-of-shift cleaning (min) | 35 | Input
Breaks with nobody covering the machine, unplanned stops (min) | 55 | Input
Reject rate | 4% | Input, as a percentage
Print-only rate (pieces per hour) |  | Closest to a rated figure
Machine cycle time (min) |  | Two fixtures: the longer of the print and the operator's loading and inspection, plus the swap. One fixture: loading, then the print
Who sets the pace |  | If the operator, more fixtures will not raise output
Available printing time (min)
Cycles in the shift
Pieces printed
Rejects
Accepted pieces per shift
Accepted output per hour of shift |  | The figure to compare between machines